## Risk Register
Risk ID | Asset / Process | Risk Statement | Key Weakness / Finding | Initial Likelihood | Initial Impact | Initial Rating | Existing / Interim Controls | Treatment | Risk Owner (proposed) | Remediation Owner (proposed) | Target Date | Status | Required Evidence / Verification | Residual Risk | Closure Criteria / Notes
EHR-001 | EHR server / patient records | An attacker could exploit a known software vulnerability on an internet-accessible EHR server to gain unauthorized access to confidential patient records. | Known vulnerability remains unpatched; exploitation of the same vulnerability is reported elsewhere in the scenario. | High | High | High (illustrative) | Vulnerability scanning; interim network restrictions proposed and tested in scenario. | Mitigate | IT / EHR system owner (to confirm) | IT infrastructure / vulnerability management (to confirm) | To be assigned urgently under policy | Open — remediation in progress | Patch deployment record; vulnerability retest; functional testing; approved change record; updated assessment. | Reassess after verified remediation; do not assume Low automatically. | Close only after patch effectiveness, required review, residual-risk assessment, and approval are documented.
EHR-002 | EHR backup and recovery | A server failure or ransomware incident could prevent access to patient records if backups cannot be restored reliably and within approved recovery requirements. | Recovery testing exceeded illustrative four-hour RTO; backups shared the production network; initial restore showed data-integrity issues. | Moderate | High | High (illustrative; validate) | Backups exist; isolated backup and revised database-consistent backup process proposed in scenario. | Mitigate | IT / business continuity owner (to confirm) | Backup / infrastructure team (to confirm) | To be assigned based on risk and policy | Open — closure review pending | Successful restoration; data integrity validation; RTO/RPO results; change records; test approval. | Reassess after successful test and governance review. | Scenario's final retest met illustrative 3-hour recovery against 4-hour RTO and 15-minute RPO; formal approval/closure requirements remain to be confirmed.
EHR-003 | Identity and access management | Former employees' accounts could allow unauthorized access to hospital systems or patient information. | Unneeded accounts remained active; access removal requires evidence of disablement. | Moderate | High | High (illustrative; validate) | Approved account-disablement process and verification. | Mitigate | IT / system owner (to confirm) | IAM / access-management team (to confirm) | Promptly according to offboarding policy | Closed in scenario — verification assumed | Access-disablement records; confirmation authentication is blocked; review of relevant sessions/tokens/privileges where applicable. | Reassess for remaining access paths. | Training scenario treated the accounts as remediated after verification; real closure requires actual evidence and required sign-off.
EHR-004 | Employee offboarding process | Without a consistently executed offboarding process, former employees' accounts may remain active beyond the required timeframe. | Unclear ownership, incorrect ticket routing, IAM backlog, and weak overdue-request escalation were found in successive simulated tests. | Moderate | High | To be assessed using approved methodology | Automatic routing; overdue escalation; access-removal evidence requirement; override logging and review proposed. | Mitigate | IAM / IT access-management manager with HR (to confirm) | IAM team / workflow administrator (to confirm) | To be assigned under policy | Ready for closure review in scenario | Routing and escalation configuration; sample test results; disablement evidence; override logs and review records. | Reassess after successful operating-effectiveness testing. | Scenario's final test: 10 of 10 sampled accounts disabled within required timeframe and escalation worked; close only after required approval.
EHR-005 | Quarterly user access reviews | If quarterly user access reviews are not performed consistently, inappropriate access may remain undetected. | Reviews were missed for six months because responsibilities were unclear; some removal tickets lacked evidence; one account remained active; override monitoring weaknesses were identified. | Moderate | High | To be assessed using approved methodology | Assigned ownership; quarterly review procedure; access-removal verification; authorized override logging and weekly monitoring proposed. | Mitigate | Department managers / system owners (to confirm) | IAM / IT access-management team (to confirm) | To be assigned according to policy | Open — investigation and remediation required | Completed review records; removal tickets; system logs; override approvals; monitoring evidence; retest results. | Reassess after access issues are resolved and control operation is validated. | Latest scenario included an undocumented override and 24-hour continued access; investigation is required before closure. Do not mark closed.

## Remediation Tracker
Action ID | Related Risk | Action / Milestone | Proposed Owner | Target Date | Status | Evidence / Acceptance Criteria | Dependency / Escalation
ACT-001 | EHR-001 | Validate and deploy corrected vendor patch through approved change process. | IT infrastructure / vulnerability management (confirm) | Urgent date to be agreed | In progress (scenario) | Patch deployed; vulnerability retest passes; EHR functional test passes. | Escalate delay due to active exploitation; maintain interim safeguards.
ACT-002 | EHR-002 | Complete backup isolation and database-consistent backup changes; perform recovery test. | Backup / infrastructure team (confirm) | Set according to approved recovery risk | Closure review pending (scenario) | Restore integrity verified; RTO/RPO targets met; test evidence reviewed. | Address data corruption root cause and formal approval.
ACT-003 | EHR-003 | Disable former employees' accounts and verify authentication is blocked. | IAM team (confirm) | Promptly under offboarding policy | Remediated in scenario | Account status/log evidence; associated access paths checked where applicable. | Escalate any account still active or signs of misuse.
ACT-004 | EHR-004 | Implement routing, overdue escalation, evidence requirements, and override monitoring for offboarding. | IAM / workflow administrator (confirm) | Set under policy | Ready for closure review in scenario | Sample test shows requests routed correctly, escalated when overdue, and disabled on time. | Confirm actual operating effectiveness and approval before closure.
ACT-005 | EHR-005 | Investigate undocumented override and continued access; remediate account; validate quarterly review and override monitoring controls. | IAM / system owner (confirm) | Urgent for active access; broader plan per policy | Open — investigation required | Logs reviewed; access status verified; root cause and corrective action documented; successful retest. | Preserve relevant logs and follow incident process if evidence indicates misuse.

## Lessons Learned
Topic | Practical lesson
Risk rating | Use the organization's approved scoring method. Illustrative High/Moderate/Low labels in this project are not formal ratings.
Prioritization | Use severity together with urgency, threat activity, patient-care consequences, exposure, existing safeguards, and obligations.
Risk owner vs remediation owner | The risk owner is accountable for managing the risk; the remediation owner performs or coordinates corrective action. They may be different people.
Temporary safeguards | An interim control may reduce exposure without eliminating the underlying weakness. Keep the risk open while remediation is incomplete.
Risk acceptance | Acceptance should be documented, time-bounded when appropriate, and approved by an authorized decision-maker. It does not equal remediation.
Evidence | A ticket, policy, or verbal statement alone may not prove that a control worked. Seek reliable implementation and operating evidence.
Control assessment | Separate design, implementation, and operating effectiveness.
Backups | Successful backup jobs do not prove recoverability. Test restoration, data integrity, RTO, and RPO.
Closure | Close a finding only after defined remediation, verification, residual-risk review, and required approvals are complete.
Limitations | This is a fictional, guided learning exercise; no actual hospital environment was assessed.